## Overview
AI Platform Engineer: 36-Week Plan
Plan start date (Monday) | 2026-10-05 | Edit this cell: all dates update
Target hours per week | 11 | Assumption: 10-12 hrs/week alongside a full-time job
Planned end date | 2027-06-13
Weeks completed | 0
Progress | 0%
Current week (by date) | 1 | Based on today's date
Total planned hours | 396
How to use
• Yellow cells are inputs. Everything else is calculated.
• Each week ends with a deliverable; mark the week Done only when it is shipped (code merged, CI green, README updated).
• If a week slips, cut scope instead of adding time. Keep the weekly ship.
• Book the CKA exam around Week 15-17. Start applying from Week 28, not Week 36; interviews show remaining gaps.
• GPU cost: rent by the hour and shut down after each session. Set billing alerts before Week 16.
• Pay and demand differ by company and city: check current data for your target titles before applying.
• v2 changes: Phase 3 grows to 10 weeks (adds LLM/GPU basics and multi-GPU inference); Docker and Compose merged; Backstage is now an optional stretch.
Phases
1. Backend & Linux | Weeks 1-8
2. Containers & Kubernetes | Weeks 9-15
3. Model Serving & GPUs | Weeks 16-25
4. Reliability & Observability | Weeks 26-33
5. Portfolio & Job Hunt | Weeks 34-36

## Weekly Plan
Week | Phase | Start | End | Focus | Tasks | Resources | Production-grade deliverable | Build in public (LinkedIn / GitHub) | Hrs | Status | Notes
1 | 1. Backend & Linux | 2026-10-05 | 2026-10-11 | Python for services | • Async/await, type hints, pytest, uv/venv • Set up ruff, mypy, pre-commit • Create repo `llm-platform` with CI skeleton | • Python docs: asyncio • Fluent Python (Ramalho), concurrency chapters • pytest docs • ruff + mypy docs | Repo template with lint, type-check, tests; GitHub Actions CI green on every push | GitHub: create public repo `llm-platform` with README roadmap and a PROGRESS.md log LinkedIn: 'Starting a 36-week journey into AI platform engineering' post with the plan and a promise of weekly updates | 11 | Not started
2 | 1. Backend & Linux | 2026-10-12 | 2026-10-18 | FastAPI core | • Routes, Pydantic v2 models, dependency injection • Structured error responses, OpenAPI docs • Write unit + API tests with httpx | • FastAPI official tutorial • Pydantic v2 docs • httpx + pytest-asyncio docs | /health and /v1/chat (stub) with typed schemas, JSON error format, 80%+ coverage | GitHub: commit schemas + tests with clear messages LinkedIn: short post, 3 things Pydantic v2 taught you about typing LLM APIs | 11 | Not started
3 | 1. Backend & Linux | 2026-10-19 | 2026-10-25 | Streaming LLM gateway | • SSE via StreamingResponse; proxy a hosted LLM API • Handle client disconnect, upstream cancel, timeouts • Connect your Next.js chat UI to it | • FastAPI StreamingResponse docs • MDN: Server-sent events • Anthropic / OpenAI streaming API docs | /v1/chat/stream that cancels upstream on disconnect; tested end to end with your UI | LinkedIn: 30-second screen recording of your UI streaming through your own gateway GitHub: tag v0.1.0 | 11 | Not started
4 | 1. Backend & Linux | 2026-10-26 | 2026-11-01 | Auth & multi-tenancy | • Hashed API keys, JWT, per-key usage metering • Threat-check against OWASP API Top 10 • Tests for every auth failure path | • OWASP API Security Top 10 • FastAPI security docs • Passlib/argon2 docs | Keys stored hashed only; usage recorded per key; auth failure tests in CI | LinkedIn: 'API key design mistakes I avoided' (OWASP lessons, no secrets shown) GitHub: add SECURITY.md | 11 | Not started
5 | 1. Backend & Linux | 2026-11-02 | 2026-11-08 | Postgres in production style | • Schema design, SQLAlchemy 2.0 async, Alembic migrations • Indexes and EXPLAIN ANALYZE • Run Postgres as CI service container | • PostgreSQL docs (indexes, EXPLAIN) • SQLAlchemy 2.0 tutorial • Alembic docs | requests/usage tables with versioned migrations; integration tests pass in CI | LinkedIn: one image, a slow query before/after EXPLAIN ANALYZE and the index that fixed it | 11 | Not started
6 | 1. Backend & Linux | 2026-11-09 | 2026-11-15 | Redis: rate limit & cache | • Token-bucket rate limiter (atomic via Lua) • Response caching, idempotency keys • Return 429 with Retry-After | • Redis docs: rate limiter patterns, Lua scripting • redis-py docs | Per-key rate limits that hold under concurrent load; tests prove no races | LinkedIn: how you built a token-bucket limiter and the race condition you caught GitHub: link the test that proves it | 11 | Not started
7 | 1. Backend & Linux | 2026-11-16 | 2026-11-22 | Linux, networking & Ansible | • systemd, processes, ss/curl/dig/tcpdump, TLS, DNS, strace basics • Automate the VM setup with an Ansible playbook (nginx, TLS, systemd unit) • Deploy gateway behind nginx + Let's Encrypt | • The Linux Command Line (Shotts) • Julia Evans' zines • Brendan Gregg: Linux performance page • Ansible docs: getting started; Jeff Geerling: Ansible for DevOps | Gateway live on a VM over HTTPS, built by an idempotent Ansible playbook; RUNBOOK.md | LinkedIn: a Linux debugging story (what curl/tcpdump revealed) GitHub: publish RUNBOOK.md and the Ansible playbook | 11 | Not started
8 | 1. Backend & Linux | 2026-11-23 | 2026-11-29 | Harden & ship v1 | • Structured logging (structlog), 12-factor config • Graceful shutdown, pagination, request IDs • Write README + architecture diagram | • 12factor.net • Release It! (Nygard), stability patterns • Python `structlog` docs | PROJECT 1: Gateway v1.0 tagged release; CI gates lint, types, tests, coverage | LinkedIn: article 'Phase 1: building a streaming LLM gateway' with architecture diagram GitHub: release v1.0.0, pin the repo on your profile | 11 | Not started
9 | 2. Containers & Kubernetes | 2026-11-30 | 2026-12-06 | Docker & Compose, done properly | • Multi-stage builds, non-root user, slim/distroless, .dockerignore, layer caching • Scan images with Trivy in CI • Compose stack (gateway, Postgres, Redis) with healthchecks, profiles, Makefile targets • Integration tests against the stack | • Docker docs: build best practices • Trivy docs • Hadolint • Docker Compose docs • Testcontainers docs | Image under 200 MB, non-root, zero critical CVEs, scan enforced in CI; `make up` boots everything and `make test-integration` passes | LinkedIn: image-size and CVE count before/after hardening your Dockerfile GitHub: polish Makefile and Compose docs | 11 | Not started | v2: Docker and Compose merged into one week.
10 | 2. Containers & Kubernetes | 2026-12-07 | 2026-12-13 | Kubernetes core | • kind cluster; pods, deployments, services, namespaces • kubectl debugging (logs, describe, exec, events) • Begin CKA course labs | • Kubernetes docs: tutorials • Kubernetes Up & Running (Burns et al.) • KodeKloud CKA course | Gateway, Postgres, Redis running on kind via plain manifests | LinkedIn: 'Kubernetes mental model for frontend developers' diagram (your unique angle) | 11 | Not started
11 | 2. Containers & Kubernetes | 2026-12-14 | 2026-12-20 | Config, Helm & Kustomize | • ConfigMaps, Secrets, probes, requests/limits, PodDisruptionBudget • Package with Helm chart; env overlays with Kustomize • Kill pods during traffic | • Kubernetes docs: configure pods, probes, PDB • Helm docs • Kustomize docs • Kubernetes Patterns (Ibryam) | Helm chart + Kustomize overlays (dev/staging/prod); pod-kill test shows zero failed requests | LinkedIn: GIF of killing pods under traffic with zero failed requests | 11 | Not started
12 | 2. Containers & Kubernetes | 2026-12-21 | 2026-12-27 | Ingress, Gateway API, TLS, scaling | • ingress-nginx and Gateway API basics • cert-manager TLS, ExternalDNS • HPA, AKS cluster autoscaler, NetworkPolicy; load test a rollout | • ingress-nginx docs • Kubernetes Gateway API docs • cert-manager docs • ExternalDNS docs | HTTPS ingress with automatic certs and DNS; HPA + node autoscaling; zero-downtime rollout proven with k6 | LinkedIn: k6 graph of a zero-downtime rollout, plus what failed first | 11 | Not started
13 | 2. Containers & Kubernetes | 2026-12-28 | 2027-01-03 | Terraform + AKS + policy scans | • Terraform modules, remote state with locking (Azure Storage) • Provision AKS, ACR, managed Postgres, managed identity • Scan IaC with Checkov/tfsec; PR plans via Atlantis or CI; read about Terragrunt, Pulumi, Crossplane | • HashiCorp Terraform tutorials • Terraform: Up & Running (Brikman) • Azure AKS docs • Checkov docs • Atlantis docs | `terraform apply` builds the full environment; IaC scan blocks insecure changes in CI; teardown script | LinkedIn: 'AKS from zero with Terraform in N minutes' plus one cost lesson GitHub: module READMEs | 11 | Not started
14 | 2. Containers & Kubernetes | 2027-01-04 | 2027-01-10 | GitOps with Argo CD | • CI: GitHub Actions build, test, scan, push to ACR (compare quickly with Azure DevOps, GitLab CI, Jenkins) • Install Argo CD on AKS; app-of-apps and ApplicationSets • Sync waves, health checks, RBAC/SSO, Argo CD Image Updater; know how Flux differs | • Argo CD docs (getting started, ApplicationSet) • GitOps and Kubernetes (Yuen et al.) • GitHub Actions docs: environments • Flux docs (comparison) | Git is the source of truth: merge to main auto-syncs staging, approval promotes prod, rollback via git revert tested | GitHub: make the GitOps repo public (no secrets) LinkedIn: Argo CD sync-tree screenshot + 'what I'd do differently' | 11 | Not started
15 | 2. Containers & Kubernetes | 2027-01-11 | 2027-01-17 | Secrets, policy & supply chain | • Azure Key Vault + External Secrets Operator + workload identity • Kyverno (or OPA Gatekeeper) policies: no root, require limits, signed images only • Sign images with cosign; generate SBOM; Pod Security Standards; Renovate/Dependabot | • External Secrets Operator docs • Kyverno docs • Sigstore/cosign docs • AKS security best practices • CKS curriculum (reference) | PROJECT 2: v2 on AKS: no secrets in Git, policies enforced at admission, signed images, SBOM. Book CKA exam | LinkedIn: article 'Phase 2: from VM to GitOps on AKS' with security checklist GitHub: release v2.0.0 | 11 | Not started
16 | 3. Model Serving & GPUs | 2027-01-18 | 2027-01-24 | LLM & transformer fundamentals | • Tokenization (BPE), embeddings, self-attention (Q/K/V), causal masking, RoPE, GQA • Build nanoGPT following Karpathy; train a tiny model on a free or cheap GPU • PyTorch basics: tensors, autograd, training loop, mixed precision, GPU memory use | • Karpathy: Neural Networks: Zero to Hero (micrograd, Let's build GPT, GPT Tokenizer) • Jay Alammar: The Illustrated Transformer • PyTorch official tutorials • Hugging Face LLM course | nanoGPT repo with training log and notes explaining each block; you can explain attention, KV cache and GQA from a whiteboard | LinkedIn: 'Attention explained for frontend developers' diagram plus your nanoGPT sample output GitHub: publish nanogpt-notes repo | 11 | Not started | New in v2: ML basics that inference roles expect.
17 | 3. Model Serving & GPUs | 2027-01-25 | 2027-01-31 | Inference fundamentals | • Prefill vs decode, KV cache, GQA, batching, attention memory • Compute KV cache size per token • Estimate max concurrency for an 8B model • Dense vs MoE memory math; arithmetic intensity and the roofline model | • kipply: Transformer Inference Arithmetic • Lilian Weng: Large Transformer Model Inference Optimization • Hugging Face LLM inference guide • Vishakha Sadhwani: The AI Inference Engineering Roadmap (use as a checklist) | Notebook computing weights + KV cache memory and max concurrency on 24 GB vs 80 GB GPU | LinkedIn: infographic 'How much memory does an LLM really need?' using your KV cache math | 11 | Not started
18 | 3. Model Serving & GPUs | 2027-02-01 | 2027-02-07 | GPU basics & first kernel | • Memory hierarchy, bandwidth- vs compute-bound • nvidia-smi, DCGM metrics, GPU selection • Write one simple kernel (vector add, then tiled matmul) in Triton or CUDA and profile it | • How to Think About GPUs (jax-ml scaling book) • Horacio He: Making Deep Learning Go Brrrr • NVIDIA CUDA programming guide, intro • GPU MODE lectures (YouTube) • Programming Massively Parallel Processors (Hwu, Kirk), early chapters • Triton tutorials | Comparison table: L4 / A10 / A100 / H100 on memory, bandwidth, $/hr, fit for 8B-70B; plus kernel repo with a profiler screenshot | LinkedIn: GPU comparison table (memory, bandwidth, $/hr) and which you'd pick for 8B | 11 | Not started
19 | 3. Model Serving & GPUs | 2027-02-08 | 2027-02-14 | Serve with vLLM | • Run vLLM OpenAI-compatible server on rented GPU • Tune max-model-len, gpu-memory-utilization • Place behind your gateway with streaming | • vLLM docs (quickstart, serving) • PagedAttention paper • RunPod / Lambda Labs docs | Self-hosted model streaming through gateway with health checks and timeouts | LinkedIn: demo video of a self-hosted model streaming through your gateway | 11 | Not started
20 | 3. Model Serving & GPUs | 2027-02-15 | 2027-02-21 | Benchmarking | • Measure TTFT, inter-token latency, throughput, concurrency 1-128 • Use vLLM benchmark scripts or GenAI-Perf • Fix a repeatable test harness | • vLLM benchmarks docs • NVIDIA GenAI-Perf docs • Locust docs | Reproducible benchmark script + committed results and charts | LinkedIn: benchmark chart, TTFT vs concurrency GitHub: commit benchmarks/ with scripts and CSVs | 11 | Not started
21 | 3. Model Serving & GPUs | 2027-02-22 | 2027-02-28 | Quantization & optimization | • FP8, AWQ, GPTQ; prefix caching; speculative decoding • Check quality with lm-evaluation-harness • Pick a recommended config | • vLLM quantization docs • AWQ paper • EleutherAI lm-evaluation-harness | Table of speed, memory, and quality across configs, with a justified recommendation | LinkedIn: quantization trade-off table; ask readers which trade-off they'd choose | 11 | Not started
22 | 3. Model Serving & GPUs | 2027-03-01 | 2027-03-07 | Multi-GPU & distributed inference | • Tensor vs pipeline vs expert parallelism: when each fits; NVLink vs PCIe impact • Collectives (all-reduce, all-gather) and NCCL basics; read GPU topology with `nvidia-smi topo -m` • Run vLLM with tensor-parallel-size 2 on a 2-GPU rental; compare TP=1 vs TP=2 on throughput and latency | • Hugging Face: The Ultra-Scale Playbook • Google/JAX: How to Scale Your Model • vLLM docs: parallelism and scaling • NVIDIA NCCL docs (overview) • Megatron-LM paper (tensor parallelism) | Benchmark of TP=1 vs TP=2, including a model that only fits with TP=2; scaling-efficiency chart and a one-page note on communication cost | LinkedIn: scaling-efficiency chart, 'What a second GPU actually buys you' GitHub: add results to benchmarks/ | 11 | Not started | New in v2: multi-GPU work is a core inference-engineer skill; needs a 2-GPU rental, so budget for it.
23 | 3. Model Serving & GPUs | 2027-03-08 | 2027-03-14 | Alternatives, routing & canary | • Try SGLang (prefix cache) against vLLM; skim TGI, TensorRT-LLM and Triton docs • Model router: self-hosted vs hosted by policy, with fallback • Canary a new model version with Argo Rollouts and metric analysis • Read NVIDIA Dynamo and llm-d docs: cache-aware routing, prefill/decode disaggregation | • SGLang docs • Hugging Face TGI docs • NVIDIA Triton docs • Argo Rollouts docs • NVIDIA Dynamo docs • llm-d docs • TensorRT-LLM docs | Gateway routes by policy; new model version promoted via automated canary and rolled back on bad metrics | LinkedIn: screenshot of an Argo Rollouts canary promoting or aborting a model version | 11 | Not started
24 | 3. Model Serving & GPUs | 2027-03-15 | 2027-03-21 | GPUs on Kubernetes & MLOps tooling | • AKS GPU node pool, taints/tolerations, NVIDIA GPU Operator • Weights cache on PVC; KServe or Ray Serve; KEDA on queue depth and KV-cache usage (not CPU) • Track model versions in MLflow registry; know where Kubeflow fits | • NVIDIA GPU Operator docs • KServe docs • KEDA docs • MLflow docs • Kubeflow docs (awareness) | vLLM as a Kubernetes deployment (via Argo CD) with cached weights, queue-based scaling, registered model version | LinkedIn: 'GPU on AKS gotchas' short list from what actually broke | 11 | Not started
25 | 3. Model Serving & GPUs | 2027-03-22 | 2027-03-28 | Cost & capacity | • Cost per 1M tokens, utilization, batch vs realtime • Install OpenCost/Kubecost for per-namespace cost • Capacity plan; self-host vs API break-even | • OpenCost docs • Chip Huyen: AI Engineering (inference chapters) • Google SRE Workbook: capacity | PROJECT 3: Serving platform report: benchmarks, cost model, OpenCost dashboard, recommended config | LinkedIn: article 'What it costs to serve an 8B model' with cost per 1M tokens GitHub: publish the report | 11 | Not started
26 | 4. Reliability & Observability | 2027-03-29 | 2027-04-04 | Tracing & the Grafana stack | • OpenTelemetry in FastAPI; trace propagation • Collector -> Tempo (traces) and Loki (logs) • Scrape vLLM Prometheus metrics | • OpenTelemetry Python docs • Grafana Tempo and Loki docs • vLLM metrics docs | One trace links gateway, queue, and vLLM timings; logs searchable by trace ID in Loki | LinkedIn: one trace screenshot following a request across layers | 11 | Not started
27 | 4. Reliability & Observability | 2027-04-05 | 2027-04-11 | Metrics, dashboards & alerting | • kube-prometheus-stack via Argo CD; RED + USE methods • DCGM GPU exporter; Alertmanager routing • Dashboards as code (JSON in repo) | • Prometheus docs • Grafana tutorials • NVIDIA DCGM exporter • Alertmanager docs | Dashboards for latency, TTFT, tokens/s, queue depth, GPU util, KV-cache utilization, error rate, cost; alerts to Slack/email | GitHub: commit dashboards-as-code LinkedIn: Grafana walkthrough, metrics you watch and why | 11 | Not started
28 | 4. Reliability & Observability | 2027-04-12 | 2027-04-18 | LLM observability | • Self-host Langfuse; trace prompts, tokens, cost • Prompt versioning • PII redaction before logging | • Langfuse docs • Arize Phoenix docs (alternative) | Every request traced with tokens, latency, cost; PII scrubbed | LinkedIn: what LLM observability showed that logs never did (tokens, cost, slow prompts) | 11 | Not started
29 | 4. Reliability & Observability | 2027-04-19 | 2027-04-25 | Evals as a CI gate | • Golden dataset, LLM-as-judge, regression tests • Promptfoo or DeepEval in CI • Run nightly eval pipelines as Argo Workflows | • Hamel Husain: Your AI product needs evals • promptfoo docs • Argo Workflows docs • AI Engineering (Huyen), evaluation chapters | Eval suite blocks merges on regression; nightly Argo Workflow reports quality trend | LinkedIn: 'Evals as a CI gate' with a screenshot of a blocked merge | 11 | Not started
30 | 4. Reliability & Observability | 2027-04-26 | 2027-05-02 | Load & soak testing | • k6/Locust with streaming connections • Soak test for leaks; find saturation point • Identify the bottleneck and fix one | • k6 docs • Locust docs • Brendan Gregg: USE method | Load-test report: max concurrent streams within SLO, bottleneck, fix, before/after | LinkedIn: draft of your key post, 'What broke at N concurrent streams' | 11 | Not started
31 | 4. Reliability & Observability | 2027-05-03 | 2027-05-09 | Resilience patterns | • Timeouts, retries with jitter, circuit breakers, bulkheads • Load shedding and graceful degradation • Chaos: kill GPU pod mid-stream | • AWS Builders' Library: timeouts, retries, backoff with jitter • Release It! (Nygard) • Google SRE book: handling overload | Fallback to hosted provider when GPU fails; chaos test automated and passing | LinkedIn: short video of the chaos test and graceful fallback | 11 | Not started
32 | 4. Reliability & Observability | 2027-05-10 | 2027-05-16 | SRE practice | • Define SLIs/SLOs and error budgets • Burn-rate alerts via Alertmanager • Runbooks and a blameless postmortem | • Google SRE Workbook: SLO chapters • PagerDuty incident response guide | SLO doc, alerts, runbooks, and a postmortem of a failure you caused on purpose | LinkedIn: a sanitized blameless postmortem of your own deliberate failure | 11 | Not started
33 | 4. Reliability & Observability | 2027-05-17 | 2027-05-23 | Security for LLM systems | • Threat model: prompt injection, data leakage, abuse • Audit logging; Trivy Operator for in-cluster scanning; Falco for runtime alerts • HashiCorp Vault concepts; OWASP Top 10 for LLM Apps checklist | • OWASP Top 10 for LLM Applications • Trivy Operator docs • Falco docs • HashiCorp Vault tutorials | PROJECT 4: Threat model doc, fixes merged, runtime and image scanning active; platform v3 released | LinkedIn: article 'Phase 4: running an LLM platform reliably' GitHub: release v3.0.0 | 11 | Not started
34 | 5. Portfolio & Job Hunt | 2027-05-24 | 2027-05-30 | Full-stack integration | • Wire your Next.js chat UI to auth, streaming, retries • Deploy a public demo env with spend limits • Record a 3-minute demo video | • Vercel AI SDK docs • Next.js deployment docs | Live demo: UI + gateway + self-hosted model, with rate limits and cost caps | LinkedIn: 3-minute demo video of the full platform with your UI; set as Featured GitHub: clean demo instructions | 11 | Not started | Stretch (optional): Backstage golden-path template (see Tools Map) only if you are ahead of schedule.
35 | 5. Portfolio & Job Hunt | 2027-05-31 | 2027-06-06 | Public content & resume | • Write 2 posts (e.g. what broke at 100 concurrent streams) • Rewrite resume around platform work with numbers (p95, tokens/s, $) • Update LinkedIn • C4 diagrams, 5+ ADRs, runbooks; polish READMEs for a hiring manager skimming in 2 minutes | • Your own benchmark data • Levels.fyi / Glassdoor for pay ranges • C4 model site • adr.github.io | 2 posts published; resume v2 with measured results; target titles on LinkedIn; architecture docs (C4, 5+ ADRs) | LinkedIn: publish your 2 best posts as articles; update headline, About, Featured GitHub: profile README linking projects | 11 | Not started
36 | 5. Portfolio & Job Hunt | 2027-06-07 | 2027-06-13 | Interview prep & apply | • System design: LLM serving platform, gateway, multi-tenant GPU • Kubernetes/Linux deep-dive questions; mock interviews • Apply to 20 roles and request internal transfer talks at EY | • System Design Interview (Alex Xu) • AI Engineering (Huyen) • killer.sh CKA mock exams | PROJECT 5: 3 practiced system designs, 20 applications sent, internal transfer conversation held | LinkedIn: 'Open to AI platform roles' post with links to projects and demo Engage with 10 relevant posts this week | 11 | Not started
Formulas:
Start = Overview!$B3+7*([Week]-1)
End = [Start]+6

## Production Bar
Area | Every project must have | Check by week | Status
Code quality | Lint, type checks, formatting enforced in CI; PR reviews even if solo (self-review checklist) | Week 1 | Not started
Testing | Unit + integration tests; coverage gate (80%+); tests run against real Postgres/Redis | Week 5 | Not started
Security | No secrets in repo; hashed keys; dependency + image scanning; least-privilege identities | Week 15 | Not started
Infrastructure as code | Everything reproducible with Terraform/Helm; no manual console changes | Week 13 | Not started
Deployments | Automated pipeline, staged environments, tested rollback, zero-downtime rollout | Week 14 | Not started
Observability | Structured logs, metrics, traces, dashboards in version control | Week 27 | Not started
Reliability | Timeouts, retries, fallback, rate limits, load-tested limits, SLOs with alerts | Week 32 | Not started
Cost | Cost per request/1M tokens tracked; billing alerts; teardown scripts | Week 25 | Not started
Documentation | README, architecture diagram, ADRs, runbooks, postmortem | Week 35 | Not started

## Tools Map
Category | Tool | Priority | Week | How you use it in this plan
GitOps / CD | Argo CD | Must | 14 | Deploy everything from Git; app-of-apps, ApplicationSets
GitOps / CD | Argo Rollouts | Must | 23 | Canary model versions with metric-based rollback
Workflows | Argo Workflows | Should | 29 | Nightly eval and batch pipelines
GitOps / CD | Flux | Awareness | 14 | Compare with Argo CD; know the trade-offs
CI | GitHub Actions | Must | 1, 14 | Build, test, scan, push images
CI | Azure DevOps / GitLab CI / Jenkins | Awareness | 14 | Port one pipeline to see differences; common in enterprises
Packaging | Helm | Must | 11 | Chart for the gateway and platform components
Packaging | Kustomize | Must | 11 | Per-environment overlays
IaC | Terraform | Must | 13 | AKS, ACR, Postgres, identities
IaC | Checkov / tfsec | Should | 13 | Block insecure infrastructure in CI
IaC | Atlantis / Terragrunt | Should | 13 | PR-based plan/apply; DRY environments
IaC | Pulumi / Crossplane | Awareness | 13 | Alternatives; Crossplane for platform APIs
Config mgmt | Ansible | Should | 7 | Reproducible VM setup
Containers | Docker + BuildKit | Must | 9 | Multi-stage, cached, non-root images
Containers | Trivy / Hadolint | Must | 9 | Image and Dockerfile scanning
Kubernetes | kubectl, kind, AKS | Must | 10-13 | Local and managed clusters
Kubernetes | KEDA | Must | 24 | Autoscale on queue depth
Kubernetes | ingress-nginx / Gateway API | Must | 12 | Traffic entry and routing
Kubernetes | cert-manager / ExternalDNS | Should | 12 | Automatic TLS and DNS
Networking | Service mesh (Istio / Linkerd) / Cilium | Awareness | 12 | Read docs; know mTLS and eBPF use cases
Secrets | Key Vault + External Secrets Operator | Must | 15 | No secrets in Git
Secrets | HashiCorp Vault | Awareness | 33 | Common in non-Azure shops
Policy | Kyverno / OPA Gatekeeper | Must | 15 | Admission policies as code
Supply chain | cosign / Sigstore, SBOM | Should | 15 | Sign and verify images
Security | Trivy Operator / Falco | Should | 33 | In-cluster scanning and runtime alerts
Observability | Prometheus + Alertmanager + Grafana | Must | 27 | Metrics, dashboards, alerts
Observability | OpenTelemetry + Tempo + Loki | Must | 26 | Traces and logs
Observability | Langfuse / Phoenix | Should | 28 | LLM tracing and cost
Cost | OpenCost / Kubecost | Should | 25 | Per-namespace and per-model cost
ML serving | vLLM, SGLang, TGI, Triton | Must | 19-23 | Model servers; vLLM as primary
ML serving | KServe / Ray Serve | Should | 24 | Serving abstraction on Kubernetes
MLOps | MLflow | Should | 24 | Model registry and versioning
MLOps | Kubeflow | Awareness | 24 | Know where it fits; rarely needed for LLM serving
Platform | Backstage | Stretch | 34 | Developer portal and golden-path templates
Reliability | k6 / Locust | Must | 30 | Load and soak tests
Reliability | Velero / backups | Awareness | 32 | Cluster and volume backup concepts for runbooks
ML serving | NCCL + vLLM tensor parallelism | Must | 22 | Serve a model across 2 GPUs; measure scaling efficiency
ML serving | NVIDIA Dynamo / llm-d | Awareness | 23 | Cache-aware routing and prefill/decode disaggregation concepts
GPU | CUDA / Triton (language) | Should | 18 | Write and profile one kernel to understand GPU performance

## Build in Public
Section | Item | Details
Setup (Week 1) | LinkedIn profile | Headline: 'Senior Frontend Engineer -> AI Platform ¦ Building LLM infra in public'. Pin a short About covering your stack and the 36-week project. Turn on Creator mode and add 3-5 topic hashtags.
Setup (Week 1) | GitHub profile | Profile README linking projects; one public monorepo or 2-3 focused repos (gateway, infra, gitops). Pin the best 4. Use a professional photo and bio.
Cadence | Weekly rhythm | Monday: post the week's goal (1-2 lines, optional). Friday: ship post with a screenshot, GIF, chart, or diagram. 30 minutes of reading and commenting on others' posts, daily is better.
Cadence | Phase recaps | One long-form LinkedIn article at the end of each phase (weeks 8, 15, 25, 33) plus a tagged GitHub release.
Post formats | What works | Before/after numbers, a mistake and its fix, a diagram, a short screen recording, a benchmark chart, a checklist. Lead with the result, then 3-5 short lines of what you learned.
Post formats | What to avoid | Generic motivation, tutorial copy-paste, vague 'I learned Kubernetes' posts, tagging big names for attention.
Your angle | Frontend-to-infra story | You already build AI chat UIs. Show the full path: the UI on top, the gateway and GPUs underneath. Few infra engineers can demo the whole stack.
GitHub hygiene | Every repo | Clear README (problem, architecture diagram, how to run, results), LICENSE, tags/releases, CI badge, issues for your own roadmap, meaningful commit messages, small weekly commits.
GitHub hygiene | Proof of production grade | Benchmarks folder, dashboards-as-code, runbooks, ADRs, SECURITY.md, postmortem, cost report. This is what separates you from tutorial repos.
Safety | Employer and secrets | Never post EY or client code, data, architecture, or names. Use only your personal projects and public data. Check your employer's social media and side-project policy. Scrub secrets, keys, IPs, and cloud account IDs from screenshots and repos.
Safety | Cost and abuse | Do not leave public demos unprotected: add rate limits, spend caps, and auth. Shut down GPU instances.
Growth | Engagement | Reply with substance to 5-10 posts a week from platform, SRE, and ML infra engineers. Follow target companies and join their engineering conversations. Thank people who give feedback and apply it.
Growth | Consistency target | 36 Friday posts, 4 articles, 4 releases, 1 demo video by Week 34. Missing a week is fine; stopping is the failure.
Measure | Track monthly | Profile views, search appearances, recruiter messages, GitHub stars/forks, and conversations started. Quality of conversations matters more than likes.